## Sheet1
Week | Semester | Task | Details
Sep 20-29 | 1 | Project Initiation and Analysis | Understanding weekly objectives. Choosing a specific chatbot functionality.
Oct 2-6 | 1 | Requirements Gathering | Choosing a set of requirements for the project. Github is ready as well as overleaf.
Oct 9-13 | 1 | Design and Planning | Wireframes, System artchitecture diagram, gannt chart development
Oct 16-20 | 1 | Design and Planning | Design and Analysis should be done before project code implementation.
Oct 23-27 | 1 | Development | Learning how to start coding the chatbot using flask, python, HTML, CSS, possibly javascript.
Oct/Nov 30-3 | 1 | Development | Implement natural language processing (NLP) techniques, as well as database.
Nov 4-14 | 1 | Development "Web Interface" | Design the chatbot interface that is accessible via the web.
Nov 14-23 | 1 | Development "Conversation History" | Design the chatbot interface that is accessible via the web. Creating a conversation history.
Nov 24-31 | 1 | Development "Option repsonses " | Develop a chatbot logic that can process user queries, provide option-based responses, and interface with the support service data.
Dec 1-10 | 1 | Development "API Integrations" | Develop a chatbot logic that can process user queries, provide option-based responses, and interface with the support service data. Possible API Integrations and Multi language Support
Dec 11-25 | Break | Dissertation | Finish the background research section in the dissertation.
Dec/Jan 26-5 | Break | Dissertation | Finish the requirement analysis, and design sections in the dissertation.
Jan 6-15 | 2 | Dissertation | Finish the implementation section in the dissertation.
Jan 16-24 | 2 | Testing | Rigorously test the chatbot's functionality. Gather feedback and make necessary adjustments.
Jan 25-31 | 2 | Documentation | Provide Documentation in the chatbot website.
Feb 1-7 | 2 | Finalizing Development | Make sure the Implementation is completely done
Feb 8-15 | 2 | Dissertation | More dissertation work.
Feb 16-24 | 2 | Evaluation | Gather feedback from surveys for improvements. Do a good evaluation of the chatbot system.
Feb 24-29 | 2 | Dissertation | Do Final touches to the Dissertation
Mar 1-15 | 2 | Presentation | Deliver the project presentation.
Mar 16-30 | 2 | Dissertation | Making sure dissertation is done.
April 1-10 | 2 | Finish | Finalize all project documentation. Submit the project.